## Utils (hidden)
Member | All | Christina Kim | Gio Canales | Lima Ibrahimkhail | Quoc Vuong

## Backlog
ExpenseSplit
Members: | Christina Kim, Gio Canales, Lima Ibrahimkhail, Quoc Vuong
Task | Description | Member | Status | Start Date | End Date | Comments
Write Final Report | Create/Write Final Report | Christina Kim | Completed | 2025-12-01 | 2025-12-01
Calendar Blank | Clear out Calendar text after a split is complete | Christina Kim | Completed | 2025-11-26 | 2025-11-26
Reminders | Local notifications when due date approaches | Christina Kim | Completed | 2025-11-07 | 2025-12-01
Fix Split Page UI | Fix seekbar UI | Gio Canales | Completed | 2025-11-17 | 2025-11-26
README | Generate readme with required information on the app | Christina Kim | Completed | 2025-11-25 | 2025-11-25
Deadline tracking | Add due date when creating an expense Store deadline in DB | Christina Kim | Completed | 2025-11-19 | 2025-11-20
Date Picker | Date selection option for expense splits | Christina Kim | Completed | 2025-11-19 | 2025-11-20
History / Archive | Past settled expenses (up to a certain date) | Christina Kim | Completed | 2025-11-18 | 2025-11-18
Expense Completion | Option that should mark the payment as completed and push it to history/remove from deadlines | Christina Kim | Completed | 2025-11-18 | 2025-11-18
Fix Save | Fix unresponsive save in split screen | Christina Kim | Completed | 2025-11-18 | 2025-11-18
Group dashboard | See list of expenses, balances, and deadlines Sort dropdown option in the deadlines (by name, date, amount, etc.) | Christina Kim | Completed | 2025-11-17 | 2025-11-17
Front Page | Design UI for front page and navigation to other fragments for expense splitting and history features | Quoc Vuong | Completed | 2025-10-09 | 2025-10-09
Project initialization | Initialize project in GitHub; create empty View | Christina Kim | Completed | 2025-09-27 | 2025-09-27
App Mockup | Design mockup of dashboard and other tabs | Quoc Vuong | Completed | 2025-09-30 | 2025-10-09
Expense creation | Add an expense (title, amount, date, payers), Choose participants & split method (equal/custom), Balance calculation | Christina Kim | Completed | 2025-10-08 | 2025-10-10
Expense storage | Database schema design CRUD operations for expenses | Christina Kim | Completed | 2025-10-18 | 2025-10-23
Custom Split | Implement method for custom splitting in the Split interface (currently only provide equal Split) | Gio Canales | Completed | 2025-10-27 | 2025-10-31
Custom Split Database | Integrate custom split with database | Christina Kim | Completed | 2025-11-02 | 2025-11-05
Scrollbar | Add scrollability to list of payers for visibility | Christina Kim | Completed | 2025-11-12 | 2025-11-13

## Read Me
To use the template
1 | Change the document name to "Group num Backlog" (e.g., Group 1 Backlog),
and share it among the members & the instructor (yan.chen01@sjsu.edu)
2 | In Backlog, enter project name and group members
Then document each task as a row:
| 2.1) | Task name (such as Brainstorming, UI Design, etc.)
| 2.2) | Describe the task in more details
| 2.3) | Choose the member who's responsible for the task
| 2.4) | Choose the status
| 2.5) | For started (In Progress) tasks, enter the start date
| 2.6) | For Completed tasks, enter the end date
| 2.7) | Enter any additional notes
3 | Hide or Delete this Read Me Page (or Move it after Backlog so Backlog is the front page)
Color Codes (auto)
Red background: |  | Error
Red text: |  | Urgent task (due soon or blocking other tasks)
Grey text: |  | Completed
The last submission should have NO red background (no error) and all taskes should be in grey (all completed)
Possible Errors
| 2 | Missing group number or group members
| 2.5) | Missing start date for an In Progress or Completed task
OR Having start date for a Not Started task
| 2.6) | Missing end date for a Completed task
OR Having end date for an uncompleted task